## Master Checklist
Production RAG Engineering — Milestone Tracker
Goal: Build the architecture in the supplied RAG diagram from fundamentals → production-grade RAG → enterprise/agentic evolution.
ID | Major Component | Milestone | Primary Deliverable | Python | TypeScript | Status | Progress % | Dependencies | Notes
M0 | Foundation | Project foundation & engineering standards | Repo structure, environments, config, logging, errors, typing, linting, tests, CI baseline | Primary | Secondary | Not Started | 0 | - | Production-quality baseline from day one
M1 | Ingestion & Indexing | Data Sources | Local PDF/DOCX/TXT + web pages; normalized source contract | Primary | Secondary | Not Started | 0 | M0 | At least 2 source implementations
M2 | Ingestion & Indexing | Connectors | File connector + web connector; connector interface and retries | Primary | Secondary | Not Started | 0 | M1 | Connector abstraction
M3 | Ingestion & Indexing | Parsing & Extraction | Document text extraction + HTML extraction; metadata model | Primary | Secondary | Not Started | 0 | M2 | Add OCR/table extraction later
M4 | Ingestion & Indexing | Chunking | Recursive/fixed chunking + semantic chunking; chunk metadata | Primary | Secondary | Not Started | 0 | M3 | Benchmark chunk strategies
M5 | Ingestion & Indexing | Embedding Generation | Cloud embedding + local embedding; provider abstraction | Primary | Secondary | Not Started | 0 | M4 | Compare quality/cost/latency
M6 | Ingestion & Indexing | Indexing & Storage | Vector index + keyword/BM25 index + document/chunk/object storage | Primary | Secondary | Not Started | 0 | M5 | Idempotent indexing
M7 | Retrieval & Generation | User Query | API/query contract, validation, request IDs, query lifecycle | Primary | Primary | Not Started | 0 | M6 | TS becomes relevant for API layer
M8 | Retrieval & Generation | Query Understanding | Preprocessing + intent detection + query rewriting + query embeddings | Primary | Secondary | Not Started | 0 | M7 | Compare simple vs LLM-assisted rewriting
M9 | Retrieval & Generation | Hybrid Retrieval | Vector + keyword retrieval; fusion, filtering, deduplication | Primary | Secondary | Not Started | 0 | M8 | Measure Recall@K
M10 | Retrieval & Generation | Reranking | Cross-encoder/reranker integration + top-K optimization | Primary | Secondary | Not Started | 0 | M9 | Measure retrieval lift
M11 | Retrieval & Generation | Context Assembly | Prompt template + context packing + token budgeting + source tracking | Primary | Primary | Not Started | 0 | M10 | Prevent context overflow
M12 | Retrieval & Generation | Generation | LLM abstraction + streaming + retries + structured response | Primary | Primary | Not Started | 0 | M11 | Provider-independent interface
M13 | Retrieval & Generation | Response & Citations | Grounded answer + citations + source metadata + failure response | Primary | Primary | Not Started | 0 | M12 | Citation correctness
M14 | Feedback & Improvement | Feedback Capture | Helpful/not-helpful feedback + query/response telemetry | Primary | Primary | Not Started | 0 | M13 | Privacy-aware feedback
M15 | Feedback & Improvement | Evaluation | Golden dataset + retrieval/answer/faithfulness/citation metrics | Primary | Secondary | Not Started | 0 | M14 | Regression suite
M16 | Feedback & Improvement | Failure Analysis | Failure taxonomy, error clustering, bad retrieval analysis | Primary | Secondary | Not Started | 0 | M15 | Root-cause workflow
M17 | Feedback & Improvement | Continuous Improvement | Re-indexing, prompt/model/chunk tuning loop | Primary | Secondary | Not Started | 0 | M16 | Controlled changes + evaluation gates
M18 | Production Engineering | Security & Guardrails | PII, prompt injection, access control, content safety, secrets | Primary | Primary | Not Started | 0 | M13 | Cross-cutting concern
M19 | Production Engineering | Observability | Tracing, logs, metrics, token/cost/latency, dashboards, alerts | Primary | Primary | Not Started | 0 | M13 | OpenTelemetry-oriented design
M20 | Production Engineering | Reliability | Timeouts, retries, circuit breakers, fallbacks, idempotency, DLQ | Primary | Primary | Not Started | 0 | M18,M19 | Failure-first engineering
M21 | Production Engineering | Performance & Cost | Caching, batching, concurrency, model routing, token budgets | Primary | Primary | Not Started | 0 | M20 | Cost per successful answer
M22 | Production Engineering | Deployment & Scaling | Docker, CI/CD, environments, horizontal scaling, async workers | Primary | Primary | Not Started | 0 | M21 | Cloud-ready architecture
M23 | Enterprise RAG | Multi-tenancy & Governance | Tenant isolation, RBAC/ABAC, data lifecycle, audit, governance | Primary | Primary | Not Started | 0 | M22 | Enterprise controls
M24 | Enterprise RAG | End-to-End Production RAG | Integrated production architecture and reference implementation | Primary | Primary | Not Started | 0 | M23 | Architecture review checkpoint
M25 | Advanced RAG | Advanced RAG Patterns | Agentic RAG, parent-child, multi-query, HyDE, graph/hybrid extensions | Primary | Primary | Not Started | 0 | M24 | Pattern trade-offs
M26 | Agentic Evolution | RAG + Agents | Tool use, MCP/A2A integration, agent routing and governed actions | Primary | Primary | Not Started | 0 | M25 | Connect to Agent Engineering phase

## Detailed Plan
Detailed Task Breakdown
Milestone | Step | Task | Implementation / Experiment A | Implementation / Experiment B | Production Engineering Focus | Exit Criteria | Status
M0 | Foundation | Repository & package structure | Python package + tests | TypeScript package + tests | Layered architecture, dependency direction | Both projects build and test cleanly | Not Started
M0 | Foundation | Engineering standards | ruff/pytest/mypy-style checks | eslint/prettier/tsc/vitest | Typing, linting, formatting, test standards | CI-quality local checks | Not Started
M0 | Foundation | Configuration & secrets | Typed settings + .env separation | Typed config + environment validation | No secrets in source; fail-fast config | Invalid config fails safely | Not Started
M1 | Data Sources | Local files | PDF/DOCX/TXT corpus | File ingestion in Node | Normalized SourceDocument contract | Multiple file types ingested | Not Started
M1 | Data Sources | Web pages | URL fetch + HTML source | Node fetch + HTML source | Timeouts, retries, size limits | Web page becomes normalized document | Not Started
M2 | Connectors | Connector abstraction | FileConnector interface | WebConnector interface | Interfaces, contracts, retry policy | Connectors swappable | Not Started
M3 | Parsing | Document extraction | PDF/DOCX/TXT extraction | HTML extraction | Parser errors + provenance | Text + metadata produced | Not Started
M3 | Parsing | Structured content | Table extraction | HTML tables | Preserve structure where useful | Tables represented safely | Not Started
M4 | Chunking | Fixed/recursive chunking | Character/token based | Equivalent TS implementation | Deterministic chunk IDs | Repeatable chunks | Not Started
M4 | Chunking | Semantic chunking | Embedding/similarity boundary method | Equivalent TS implementation | Fallback strategy + limits | Quality comparison complete | Not Started
M5 | Embeddings | Cloud embeddings | Provider SDK | Node provider SDK | Provider abstraction, rate limits | Common embedding interface | Not Started
M5 | Embeddings | Local embeddings | Local model | Local/Node-compatible option | Model versioning + dimension validation | Cloud vs local benchmark | Not Started
M6 | Indexing | Vector index | pgvector/Qdrant-style index | Node client | Idempotency + consistency | Vector search works | Not Started
M6 | Indexing | Keyword index | BM25/full-text | Postgres/Node equivalent | Index refresh strategy | Keyword search works | Not Started
M7 | Query | Query API | FastAPI endpoint | Node/NestJS-style endpoint | Validation, correlation ID | Stable API contract | Not Started
M8 | Query Understanding | Preprocessing | Normalize query | Normalize query | Input limits + injection-aware preprocessing | Deterministic normalization | Not Started
M8 | Query Understanding | Query rewriting | Rule/template rewrite | LLM-assisted rewrite | Bounded retries + fallback | Rewrite improves retrieval | Not Started
M9 | Hybrid Retrieval | Vector retrieval | Top-K semantic search | Top-K semantic search | Filters, tenant scope | Vector recall measured | Not Started
M9 | Hybrid Retrieval | Keyword retrieval | BM25/full-text | Equivalent retrieval | Filters + exact-match behavior | Keyword recall measured | Not Started
M9 | Hybrid Retrieval | Fusion | RRF/weighted fusion | Same algorithm in TS | Deduplication + score normalization | Hybrid beats baseline | Not Started
M10 | Reranking | Reranker A | Cross-encoder | API/local equivalent | Timeout + fallback | Measured reranking lift | Not Started
M10 | Reranking | Reranker B | LLM-based reranking experiment | LLM-based reranking experiment | Cost/latency guardrails | Trade-off documented | Not Started
M11 | Context | Context packing | Top-K context | Token-aware context | Token budget enforcement | No context overflow | Not Started
M11 | Context | Prompt construction | Versioned prompt template | Versioned TS template | Prompt version metadata | Prompt reproducible | Not Started
M12 | Generation | LLM provider A | Cloud LLM | Cloud LLM | Timeouts, retries, streaming | Provider abstraction | Not Started
M12 | Generation | LLM provider B | Alternative/local LLM | Alternative/local LLM | Normalized errors/metadata | Provider comparison | Not Started
M13 | Citations | Source attribution | Chunk IDs → source references | Same response model | Citation validation | Every factual claim has source where required | Not Started
M14 | Feedback | User feedback | Helpful/not helpful | API event capture | PII minimization | Feedback persisted | Not Started
M15 | Evaluation | Retrieval evaluation | Recall@K, MRR/nDCG | Evaluation service/API | Golden dataset versioning | Baseline metrics established | Not Started
M15 | Evaluation | Generation evaluation | Faithfulness, relevance, citation correctness | Evaluation endpoint | Regression thresholds | Automated eval report | Not Started
M16 | Failure Analysis | Failure taxonomy | Retrieval/generation failure classes | Dashboard/API view | Root-cause metadata | Failures categorized | Not Started
M17 | Continuous Improvement | Re-index loop | Update → chunk → embed → index | Async job trigger | Idempotent jobs + versioning | Safe re-indexing | Not Started
M18 | Security | Prompt injection | Detection + isolation | Middleware/guard | Defense in depth | Attack suite passes baseline | Not Started
M18 | Security | Access control | Document-level authorization | API authorization | Tenant isolation | Unauthorized data never retrieved | Not Started
M19 | Observability | Tracing | OpenTelemetry-style spans | OpenTelemetry-style spans | End-to-end trace correlation | Trace query lifecycle | Not Started
M19 | Observability | Metrics | Latency/tokens/cost/retrieval metrics | Service metrics | SLIs/SLOs + alerts | Dashboards show key signals | Not Started
M20 | Reliability | Resilience | Retries/timeouts/fallbacks | Same patterns in TS | Circuit breakers, bulkheads, idempotency | Failure tests pass | Not Started
M21 | Performance | Caching | Embedding/retrieval/LLM caches | Node cache layer | Cache invalidation + safety | Latency/cost reduced | Not Started
M21 | Performance | Concurrency | Batching + async workers | Node async/concurrency | Backpressure + rate limits | Throughput benchmark | Not Started
M22 | Deployment | Containerization | Docker + service | Docker + Node service | Immutable builds + health checks | Deployable artifacts | Not Started
M23 | Governance | Audit & lifecycle | Audit events + retention | API audit middleware | Data retention + deletion | Governance controls documented | Not Started
M24 | Production RAG | Integrated system | Full Python reference | Full TS application layer | Architecture, SLOs, security, observability | Production readiness review | Not Started
M25 | Advanced RAG | Advanced retrieval patterns | Multi-query/HyDE/parent-child | TS orchestration variants | Use-case driven selection | Pattern benchmark | Not Started
M26 | Agentic Evolution | RAG + agents | Tool-aware RAG | MCP/A2A-ready orchestration | Guarded actions + human approval | Agentic RAG demo | Not Started

## Architecture Coverage
Coverage Against Supplied RAG Architecture
Architecture Area | Diagram Step | What We Implement | Minimum Demos | Advanced Evolution | Primary Language | Status
Ingestion & Indexing | 1. Data Sources | Files + web pages; normalized source model | 2 | DB, API, email, knowledge bases | Python | Not Started
Ingestion & Indexing | 2. Connectors | File + web connectors | 2 | Connector registry + async ingestion | Python | Not Started
Ingestion & Indexing | 3. Parsing & Extraction | PDF/DOCX/TXT + HTML extraction | 2 | OCR, tables, metadata, language | Python | Not Started
Ingestion & Indexing | 4. Chunking | Recursive/fixed + semantic | 2 | Parent-child, structure-aware | Python | Not Started
Ingestion & Indexing | 5. Embedding Generation | Cloud + local embeddings | 2 | Model routing/versioning | Python | Not Started
Ingestion & Indexing | 6. Indexing | Vector + keyword/BM25 | 2 | Distributed vector DB, index versioning | Python | Not Started
Retrieval & Generation | 1. User Query | Validated API/query contract | 2 | Multi-tenant API | Python + TS | Not Started
Retrieval & Generation | 2. Query Understanding | Preprocessing + rewriting | 2 | Intent routing, multi-query, HyDE | Python | Not Started
Retrieval & Generation | 3. Retrieval (Hybrid) | Vector + keyword + fusion | 2 | Filters, query routing, hybrid tuning | Python | Not Started
Retrieval & Generation | 4. Reranking | Cross-encoder + LLM reranking | 2 | Adaptive reranking | Python | Not Started
Retrieval & Generation | 5. Context Assembly | Prompt + top-K + token budget | 2 | Context compression / packing | Python + TS | Not Started
Retrieval & Generation | 6. Generation | Provider abstraction + streaming | 2 | Model routing/fallbacks | Python + TS | Not Started
Retrieval & Generation | 7. Response + Citations | Grounded response + citations | 2 | Claim-level attribution | Python + TS | Not Started
Feedback & Continuous Improvement | Feedback | Helpful/not-helpful + analytics | 2 | Implicit feedback | Python + TS | Not Started
Feedback & Continuous Improvement | Failure Analysis | Failure taxonomy + analysis | 2 | Automated clustering/root cause | Python | Not Started
Feedback & Continuous Improvement | Evaluation | Retrieval + generation eval | 2 | Continuous regression gates | Python | Not Started
Feedback & Continuous Improvement | Optimization | Re-index/model/prompt/chunk tuning | 2 | Experimentation/A-B testing | Python + TS | Not Started
Cross-Cutting | Guardrails & Safety | PII, injection, access control, safety | 2+ | Policy engine + defense in depth | Python + TS | Not Started
Cross-Cutting | Observability | Tracing, logs, metrics, cost, alerts | 2+ | SLOs + distributed tracing | Python + TS | Not Started

## Technology Plan
Technology Plan — Deliberate Use of Python + TypeScript
Layer | Python Choice | TypeScript Choice | Initial Recommendation | Why | Status
Core language | Python 3.x + typing | TypeScript + Node.js | Python first | Best ecosystem for document/NLP/RAG experimentation | Planned
API | FastAPI | NestJS/Express/Fastify-style | Both | Compare AI service vs application service patterns | Planned
Parsing | Python document ecosystem | Node parsers/fetch | Python | Broader document processing ecosystem | Planned
Embeddings | Provider SDK + local models | Provider SDK | Python | Best for model experimentation | Planned
Vector store | pgvector/Qdrant-compatible | Same DB client | Both | Same retrieval concepts, different client layers | Planned
Keyword search | BM25 / PostgreSQL FTS | PostgreSQL FTS | Both | Hybrid retrieval needs both signals | Planned
LLM | Provider SDK / abstraction | Provider SDK / abstraction | Both | Provider-neutral generation contract | Planned
Evaluation | Python eval tooling | TS evaluation service | Python | Rich experimentation and analysis | Planned
Observability | OpenTelemetry | OpenTelemetry | Both | Same cross-language telemetry model | Planned
Deployment | Docker | Docker | Both | Production parity | Planned

## Progress Dashboard
RAG Project Progress Dashboard
Tracking model | Update Status + Progress % in Master Checklist; dashboard formulas update automatically.
Area | Milestones | Completed | In Progress | Blocked | Average Progress
Foundation
Ingestion & Indexing
Retrieval & Generation
Feedback & Improvement
Production Engineering
Enterprise RAG
Advanced RAG
Agentic Evolution
Overall

## Project Principles
Project Engineering Principles
# | Principle | How we will apply it
1 | Production quality from the beginning | No throwaway code: typed contracts, modular design, tests, logging, configuration, error handling and documentation are introduced from the first milestone.
2 | Understand before abstracting | Implement important RAG mechanics directly before relying heavily on frameworks such as LangChain/LlamaIndex.
3 | Two implementations per major concept | Use two concrete approaches wherever practical so trade-offs become explicit rather than theoretical.
4 | Python + TypeScript intentionally | Python is primary for document/NLP/RAG experimentation; TypeScript is primary where application/API/streaming/agent integration is advantageous.
5 | Measure everything important | Latency, cost, retrieval quality, answer quality, failure rate and throughput become first-class engineering signals.
6 | Security is not an afterthought | Tenant isolation, authorization, prompt-injection defense, PII controls and secrets management are designed into the architecture.
7 | Every milestone has an exit criterion | We don't move forward merely because code runs; the milestone must be testable and demonstrably complete.
8 | Evolve the same system | The project starts as a small RAG application and evolves into an enterprise-grade RAG platform rather than becoming disconnected demos.